## Task Tracker
Real-Time Demand Forecasting & Inventory Optimization Platform — 20-Day Build Tracker
Mark the Done column as Yes when a task is completed. Status auto-highlights.
Day | Phase | Task | Details / Sub-steps | Done (Yes/No) | Notes
1 | 1. Data Collection | Project setup | • Create GitHub repo with clean folder structure (data/, notebooks/, src/, api/, dashboard/, models/) • Set up Python virtual environment & requirements.txt • Install core libraries: pandas, numpy, scikit-learn, matplotlib • Write initial README with project goal and architecture diagram | No
1 | 1. Data Collection | Identify & gather data sources | • Find/download historical sales dataset (e.g. Kaggle demand forecasting dataset) • Identify weather data source (API or historical CSV) • List holiday calendar source for target region • Note product details, price/promotion fields needed | No
2 | 1. Data Collection | Collect remaining data | • Pull weather data for matching date range • Build/download holiday calendar dataset • Gather product metadata (category, price, promotions) • Save all raw files into data/raw/ folder | No
2 | 1. Data Collection | Initial data audit | • Load each dataset in a notebook and check shape, dtypes, date ranges • Check for overlapping keys (date, product_id, store_id) across sources • Document data dictionary (column meanings) in README | No
3 | 2. Data Processing & Feature Engineering | Exploratory Data Analysis | • Plot demand trends over time (overall & by product) • Check seasonality, holidays effect, weather correlation • Identify missing values, outliers, duplicate rows • Summarize EDA findings in notebook with charts | No
4 | 2. Data Processing & Feature Engineering | Data cleaning | • Handle missing values (imputation strategy per column) • Detect & treat outliers • Standardize date formats and merge all sources into one table • Encode categorical variables (product, store, category) | No
5 | 2. Data Processing & Feature Engineering | Feature engineering | • Create time-based features (day of week, month, is_holiday, is_weekend) • Create lag features (t-1, t-7, t-14, t-30 demand) • Create rolling stats (rolling mean/std over 7/14/30 days) • Normalize/scale numerical features | No
6 | 2. Data Processing & Feature Engineering | Build feature store & train/test split | • Save processed dataset to data/processed/ • Create reusable feature engineering pipeline (functions/classes) • Split data into train/validation/test (time-based split, not random) • Save split datasets for model training | No
7 | 3. Model Development | Baseline model | • Train simple baseline: naive forecast / moving average • Train Linear Regression model as first ML baseline • Evaluate with MAE, RMSE, MAPE • Log baseline results in a comparison table | No
8 | 3. Model Development | Tree-based models | • Train XGBoost model • Train LightGBM model • Compare feature importance across models • Log metrics for both models | No
9 | 3. Model Development | Deep learning model | • Prepare sequence data for LSTM/TCN • Build & train LSTM (or TCN) model in PyTorch • Evaluate against tree-based/baseline models • Save all trained model artifacts | No
10 | 3. Model Development | Hyperparameter tuning & cross-validation | • Set up time-series cross-validation • Tune XGBoost/LightGBM hyperparameters (Optuna or GridSearch) • Select best-performing model based on validation metrics • Document final model choice & reasoning | No
11 | 4. Prediction & Inventory Optimization | Prediction pipeline | • Build script/function to generate demand forecast for new data • Wrap forecasting logic into a reusable predict() module • Test prediction pipeline end-to-end on sample data | No
12 | 4. Prediction & Inventory Optimization | Inventory optimization logic | • Implement safety stock calculation • Implement reorder point / recommended stock logic • Implement stockout probability estimation • Validate outputs against sample scenarios | No
13 | 4. Prediction & Inventory Optimization | Integrate forecast + inventory | • Combine forecast output with inventory optimization module • Generate sample end-to-end output (forecast -> stock recommendation) • Write unit tests for core functions | No
14 | 5. Deployment | Build FastAPI backend | • Create FastAPI project structure (api/) • Build /forecast endpoint • Build /inventory endpoint • Add request/response validation with Pydantic | No
15 | 5. Deployment | Build dashboard (UI) | • Choose dashboard tool (Streamlit/Plotly Dash) • Build Overview page with KPIs (predicted demand, recommended stock, stockout %) • Build Forecast chart (actual vs forecast, next 7 days) • Add Top Insights panel & Download Report button | No
16 | 5. Deployment | Add caching & real-time ingestion | • Set up Redis for caching frequent queries • Add real-time/simulated data ingestion endpoint • Connect dashboard to FastAPI backend | No
17 | 5. Deployment | Containerize & deploy | • Write Dockerfile for API and dashboard • Test containers locally with docker-compose • Deploy to cloud (AWS / Render / Railway) • Verify live endpoints and dashboard access | No
18 | 6. Monitoring & Retraining | Set up MLflow | • Integrate MLflow for experiment tracking & model versioning • Log all trained models with parameters & metrics • Set up model registry for production model | No
19 | 6. Monitoring & Retraining | Monitoring & alerting | • Track model performance over time (drift detection) • Set up automated retraining trigger/schedule • Configure alerting (email/Slack) for failures or drift | No
20 | 7. Documentation & Wrap-up | Final polish & submission | • Write full README (setup, architecture, how to run, screenshots) • Clean up repo structure & remove unused files • Push final code to GitHub with proper commit history • Record short demo walkthrough (optional) & final review | No

## Progress Summary
Progress Summary
Total Tasks | 22
Completed (Yes) | 0
In Progress | 0
Not Started (No) | 22
% Complete | 0%
Day-wise Phase Breakdown
Phase | Days
1. Data Collection | Day 1–2
2. Data Processing & Feature Engineering | Day 3–6
3. Model Development | Day 7–10
4. Prediction & Inventory Optimization | Day 11–13
5. Deployment | Day 14–17
6. Monitoring & Retraining | Day 18–19
7. Documentation & Wrap-up | Day 20